## Sheet1
2017-2018 IDP/BUDGET/ SDF/ PMS HGDM DRAFT FRAMEWORK PLAN
Activity / Item | Description | Binding Legislation | Project Period
|  |  | July 2018 |  |  |  | Aug 2018 |  |  |  | Sept 2018 |  |  |  | Oct 2018 |  |  |  | Nov 2018 |  |  |  |  | Dec 2018 |  |  |  | Jan 2019 |  |  |  | Feb 2019 |  |  |  | March 2019 |  |  |  | April 2019 |  |  |  | May 2019 |  |  |  | June 2019
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Initiate IDP/Budget/OPMS/ SDFPlanning Cycle 2018/19 ( IDP Alignment 1st Meeting) | Planning Cycle Commences, Co-ordination & Preparation of IDP/Budget/OPMS Process | MFMA Section 53 & Section 63 | bar: July 2018 3
Prepare Process Plan for the development of the 2019-2020 IDP /Budget/OPMS & SDF Review | Prepare the draft IDP/ Budget/ PMS process plan for exco's approval | bar: July 2018 2 to Sept 2018 4
Publicise the draft IDP Process Plan |  | Municipal Systems Act | bar: July 2018 2 to Sept 2018 4
Submission of the 2019-2020 Draft IDP Process Plan to council | To allow the new Council to engage with the IDP/SDF so as to confirm the extents into which it adresses their new mandate | bar: Aug 2018 4
Submission of draft IDP Process Plan to COGTA | In order to allow Cogta an opportunity to comment on the Draft Process Plan | bar: July 2018 4; Sept 2018 4
IDP Alignment Committee 2nd meeting to discuss comments from COGTA | Aligning of the Process Plan with that of Local Munucipalities | bar: Aug 2018 3; Sept 2018 4
Submit the 2019-2020 Final IDP Process Plan to council for adoption |  | Municipal Systems Act | bar: Aug 2018 4 to Sept 2018 4
Submisson of the IDP Process Plan to COGTA and Council | bar: Aug 2018 4
Review of Community Based Plan |  |  | Nov 2018 1: Alignment of the CDP to the municipal vision and development of the Strategic Objectives
1st IDP Representative Forums | To discuss key issues that relates to Sector departments so as to influence their decisions |  | Sept 2018 3: 1st Sector Department meeting; Nov 2018 4: 2st Sector engagement by Nov. 2016
Submission of the 2017-2018 Draft Annual Report, APR and AFS to Council and the AG |  |  | Aug 2018 4: Submission of the Annual Report to Council and the AG
Submission of the 1st quarter performance report for the 2018-2019 FY | Municipal Systems Act No 32 of 2000 |  | Oct 2018 2: 1st quarter Report from departments
3nd IDP Aignment Committee | Identify key issues that require aligment and synergy with Sector Departments and other stakeholders, and to further discuss the IDP Road-Shows |  | Sept 2018 3: Preparation for the Rep Forum; Oct 2018 1: HGDM IDP Road-Shows; Oct 2018 2: Umzimkhulu IDP Road-Shows; Oct 2018 3: DR. NDZ IDP Road-Shows; Oct 2018 4: Greater Kokstad IDP Road-Show
IDP Road-Shows |  | Chapter 4 of the MSA | bar: Oct 2018 4
IDP Key Elements | Analysis of key IDP perspective in preparation for the development of a long term objectives and strategies. |  | Nov 2018 1: Analysis of the key IDP perspectives
Strategic Matrix/ Scorecard | Submit the IDP Strategic Matrix/ Scorecard to budget for budgeting purposes |  | Nov 2018 4: Host Strat Plan Session to develop the strategic matrix Budget
Review Budget, HR and PMS policies | To influence performance in the last half of the financial year |  | March 2019 1: Policy Review
Submit the Mid-Year Performance Report and adjustment budget to Provincial and National Treasury | Take into account the mid-year performance report in order to review the strategies |  | Jan 2019 2: Mid-Year Performance Assesment; Jan 2019 4: Review the IDP strategies and Submit the Annual report for Council Adoption.
Submit the Annual Report to Council for approval |  | Sect 21 of the MFMA | Jan 2019 4: Annual Report to Council
Make public the Annual Report |  | Municipal Finance Management Act | bar: Jan 2019 4
Submission of the oversight report to MPAC | As per secular 63 of the MFMA |  | Jan 2019 2: Determination of Revenue and Policies; March 2019 4: Submit to Counil the oversight report on Annual Report
Determination of Revenue and Policies
Prepare IDP/Budget/ SDF and PMS for review process | A special focus is given to the Strategic or 3 year implementation plan in the IDP
IDP Sector engagment meeting for the entire HGDM | To ensure proper alignment of all the activites and solicit implementation plans from other stakeholders to be included in the IDP |  | March 2019 1: 2nd Sector engagement meeting organised by Cogta
Table draft IDP/Budget/SDBIP to Council and Cogta | To seek approval of the draft IDP/Budget,SDF, Scorecard and SDBIP and submigt to Cogta |  | March 2019 4: Tabling of the draft IDP/Budget, SDF,SDBIP and the Organisational Scorecard to Council and Cogta
Make public the IDP/PMS and SDF |  |  | April 2019 1: Make public the IDP; Budget and SDF
IDP, Budget, SDF and SDBIP Roadshows | The Mayor embarks on the IDP/Budget roadshows to solicit comments on the draft IDP/Budget and SDBIP |  | April 2019 1: GKM LM IDP Road-Shows; April 2019 2: DNDZ LM IDP/Budget Road-Shows; April 2019 3: UBuhlebezwe LM IDP/Budget Road-Shows; April 2019 4: Umzimkhulu IDP/Budget Road-Shows; May 2019 1: HGDM IDP/Budget Road-Shows
IDP/SDF Assessments |  |  | April 2019 2: IDP Assessments by Cogta
Finalising the Draft IDP/Budget PMS | Formulation of new council prioirities |  | Feb 2019 1: Finalise IDP
IDP/PMS/Budget and oversight report
Dpt finalise submissions of Capital and Operational Exp based on the IDP/Budget Roadshows and comments from Cogta | The Acounting Officer tables comments to the HODs so as to ammend the IDP/ Budget and SDBIP accordingly |  | May 2019 1: Begin finalising the IDP/Budget/ SDF and SDBIP as per community and Cogta's comments
Submission of the 3rd quarter reports | Prepare and submit to EXCO the 3rd quarter reports and the POEs |  | April 2019 2: SDBIP 3rd quarter reports to EXCO
District IDP Assessments | Report on Performance Auditing System through IDP Rep Forum | bar: March 2019 1
District IDP Assements
Advertise the Draft IDP for public comments (21 days)
Submit IDP, Budget & SDBIP to Council | present final Budget/ IDP & draft SDBIP. Advertise Public Participation. Submit t Budgets to National & Provincial Treasury, DCOGTA & other Stakeholders | MFMA Section 22 | May 2019 3: Submissions
Submission of the SDBIP to the Mayor within 14 days | Signing of Performance Agreements and publicising | bar: Feb 2019 1 to March 2019 4; June 2019 1 to June 2019 4
Mayor submit the SDBIP to Council within 28 days | bar: June 2019 2
SDBIP submission by the Mayor to Council
Advertise SDBIP & Performance Agreements within 14 days after Council
Submission of SDBIP and Performance Agreements to CoGTA
Implementation of the IDP/Budget